## Sheet1
Epic | Category | Status | Priority | Owner | Effort (Days) | Dependencies | Notes | Details
Enterprise Auth (Org/Workspace/RBAC) | Done & Configured | ✅ Done | High |  |  | None | Routes active, tested end to end | Full org → workspace → user hierarchy with OWNER/MEMBER roles plus custom roles, backed by enterprise/rbac and workspace/role/organization routes. Registration, login, invites, and role assignment are all live against Neon database — verified end-to-end during 2026-06-30 setup. Nothing further closes this out; future work is additive (e.g. ABAC), not remedial.
Email invites (SMTP) | Done & Configured | ✅ Done | Medium |  |  | SMTP credentials | Gmail SMTP configured | User-invite emails send through Gmail SMTP (SMTP_HOST=smtp.gmail.com), so /api/v1/account/invite delivers a real, clickable invite link. Fully working; only future risk is Gmail's send-rate limits at higher volume, at which point swapping to a dedicated transactional provider (e.g. Brevo) would be a config change, not new code.
File/Blob storage (ImageKit) | Done & Configured | ✅ Done | Medium |  |  | ImageKit keys | Needs smoke test verification | Uploads stored on ImageKit's CDN (STORAGE_TYPE=imagekit) instead of ephemeral local disk. Implementation was hand-rolled since no official multer-imagekit package exists. Per rules/changes.md it has never been runtime-verified — closing this out means one actual upload + retrieval smoke test, not writing new code.
Database (Neon Postgres) | Done & Configured | ✅ Done | High |  |  | None | Migrations run automatically | Primary datastore; TypeORM migrations run automatically on every server start against Neon-hosted Postgres. This is the one dependency every other feature sits on top of — confirmed running, no outstanding work.
LLM Observability (Langfuse) | Built, Not Configured | 🟡 Pending Config | High |  | 1 | Langfuse API key | No project/API key created yet | Flowise ships a native Langfuse analytic node that traces every LLM call automatically once wired. Nobody has created a Langfuse project or entered its API key, so zero traces exist today. This is the single highest-value "flip the switch" item — entire observability story for cost tracking and debugging, takes a signup + one credential entry, not development.
Metrics (Prometheus/OpenTelemetry) | Built, Not Configured | 🟡 Pending Config | Medium |  | 1 | ENABLE_METRICS env var | Needs Grafana dashboard setup | Server-side metrics plumbing exists (Prometheus.ts, OpenTelemetry.ts, enterprise middleware), but ENABLE_METRICS is unset so it's inert. Turning on requires ENABLE_METRICS=true + METRICS_PROVIDER, collector endpoint, and building a Grafana dashboard — code only exposes metrics, doesn't visualize them.
SSO (Auth0/Azure AD/Google) | Built, Not Configured | 🟡 Pending Config | High |  | 2 | OAuth client ID/secret | Only email+password works today | SSO integration code exists for Auth0, Azure, Github, Google in enterprise/sso/, but none has client ID/secret configured — all users log in with email+password only. Enabling one is an app registration in provider's console plus dropping client ID/secret into config — no code changes required.
Vector store (Qdrant) | Built, Not Configured | 🟡 Pending Config | High |  | 1 | Qdrant instance | No instance provisioned | Qdrant is a first-class vector store node alongside 15+ others, and Document Store service handles chunking/ingestion. No Qdrant instance provisioned, no credential created, Document Store empty — pure setup work (provision instance, add credential, ingest documents) whenever RAG-backed agents are needed.
Tool credentials (Gmail, Jira, etc.) | Built, Not Configured | 🟡 Pending Config | High |  | 3 | OAuth apps registration | Zero tool credentials exist | Tool layer covers Gmail, Google Drive/Docs/Sheets/Calendar, Jira, MS Teams/Outlook, Composio, MCP, custom REST — all backed by encrypted credential store and OAuth2 routes. Zero OAuth apps registered, zero credentials exist — every tool node visible but unusable until OAuth app + credential set up per-integration.
Queue mode (parallel execution) | Built, Not Configured | 🟡 Pending Config | Medium |  | 0.5 | MODE=queue env var | Redis URL already in .env | BullMQ-based queue worker mode exists for parallel flow execution, Redis URL (Upstash) already in .env — but MODE=queue never set, server runs single-process. Turning on is one env var + starting worker process; only necessary once concurrent flow volume becomes a bottleneck.
Centralized tool-call governance | To Be Built | 🔴 To Build | High |  | 3 | RBAC foundation | Policy layer for tool access control | Nothing today enforces which agent/tenant can call which tool under what data-handling policy; credentials scoped per-node/per-user with no aggregate view or runtime policy check. This is the one capability the plan's "Arcade" layer legitimately adds. Scope: policy layer intercepting tool calls, checking per-tenant/per-agent allowlist, optionally applying DLP rules — genuinely new development.
Admin/Governance dashboard | To Be Built | 🔴 To Build | High |  | 4 | Governance layer | Agent inventory, approvals, budgets UI | RBAC and workspace management exist as APIs and basic UI, but no single screen showing agent inventory, ownership, pending approvals, or budget status — the control-tower view Stage 10 (Admin Center) and Master Feature Checklist category (e) call for. Scope: new UI screens in packages/ui React app plus supporting endpoints — largest single backlog item.
Audit log + compliance export | To Be Built | 🔴 To Build | High |  | 2 | None | Append-only trail for compliance | No append-only record of agent decisions or tool calls exists — no way to reconstruct who/what triggered a given action. Scope: audit-event table populated at every consequential action (tool call, credential use, RBAC change), plus export path for SIEM/eDiscovery — matches Master Feature Checklist category (d).
Agent lifecycle gating | To Be Built | 🔴 To Build | Medium |  | 2.5 | Evaluations framework | Draft → validated → published flow | Evaluations framework (services/evaluations, LLM-as-judge, cost tracking) exists and works, but nothing uses its output to block flow publishing — evaluation and publishing disconnected today. Scope: draft → validated → published state on flows, promotion requires passing eval thresholds — mostly wiring existing pieces together.
Cost/FinOps budgets per workspace | To Be Built | 🔴 To Build | Medium |  | 3 | Workspace RBAC | Token/spend budget alerts | No per-tenant token/spend budget, no alerting when approached or exceeded — cost visible only after the fact (once Langfuse on) and only per-call, not aggregated per workspace with limits. Scope: budget table per workspace, running-total counter fed by trace/usage data, threshold-based alerts (80% warn, 100% block) — matches plan's FinOps Phase 2.